## Slide 1: Unit 6: Managing a Successful Business Project Unit 4: Research Project Unit 18: Researching Current Issues in Aviation
Dwayne Cargill
Lecturer
Colbourne College
January 30, 2017

## Slide 2: Content
Learning Outcome 1:
  Establish project aims, objectives and timeframes based on the chosen theme.
  Examine appropriate research methodologies and approaches as part of the research process.
  Understand methodology for researching complex current issues affecting the aviation industry

## Slide 3: Learning Objectives
At the end of this session, Learners should be able to:
  AC 1.5: Provide an appropriate plan and procedures for the agreed research specification
  P4 Produce a research project management plan that covers aspects of cost, scope, time, quality, communication, risk and resources
  AC 2.1: Match resources efficiently to the research question or hypothesis
  M1 Produce a comprehensive project management plan, milestone schedule and project schedule for monitoring and completing the aims and objectives of the project.

## Slide 4: AC 1.5: Provide an appropriate plan and procedures for the agreed research specification. P4: Produce a research project management plan that covers aspects of cost, scope, time, quality, communication, risk and resources

## Slide 5: Developing a Research Plan
According to The Audience Agency (2012) before conducting any research, you should develop a research plan.
The research plan should include:
  the overall purpose of the research and how the outputs will be used and communicated;
  the types and sources of data needed (including any secondary sources and definitions of the subjects of the research);
  the means by which the data will be collected and analysed;
  the scale of research (i.e. the numbers and spread of the research subjects and the populations you want to draw conclusions about);
  the resources available (including time);
  and, a clear indication of the stakeholders in the process.
Basically, the research plan should provide answers to the following questions.

## Slide 6: Research Strategy
Write.com (n.d.) notes that you should answer three questions in developing your research strategy.
  What amount of research do you need?
    Know the length of your research and the number of sources required.
  What types of sources are appropriate for your topic?
    Primary research required and current sources.
  What types of materials are you permitted or required to use?
    Academic sources

## Slide 7: Establish a Timetable
Once you have asked the three research strategy questions, establish a timeline. The biggest consideration is the due date of your research paper. This sets the pace for how quickly you conduct research to continue working through the research writing process. Write.co (n.d.) purports these guidelines:
  Allow adequate time to conduct thorough research
  Start as soon as possible to eliminate stress that is likely to build at the last minute
  Remember that researching well and finding the right sources of information takes time

## Slide 8: Process for agreeing Project Timelines
Having developed the activities for the project, one must then seek to agree the project timeline. According the Project Management Body of Knowledge (PMBOK) Guide project managers must:
  Sequence activities
  Determine activity dependencies and construct network representation of the project activities
  Estimate activity duration

## Slide 9: Elements of the Management Plan
The Project Management Plan (PMP) is a formal, approved document used to manage project execution. The PMP documents the actions necessary to define, prepare, integrate and coordinate the various planning activities. The PMP defines how the project is executed, monitored and controlled, and closed (ucdavis.edu, n.d.).
You need to identify what are the objectives of your research/project and then decide what activities will need to be completed to achieve the research objectives. For example, to answer your research question, you will need to develop a questionnaire.

## Slide 10: Elements of the Management Plan
Having establish the activities, you need to decide what are the resources, cost, quantity, risk and level of communication that will be required for the research project to be completed on time.
Resources: a stock or supply of money, materials, staff, and other assets that can be drawn on by a person or organization in order to function effectively. Resources needed to complete a research may include questionnaires, computer and software for analysis and interviewers.

## Slide 11: Project Budget
Developing the project budget is a process for allocating administered and departmental funds necessary to build a financial foundation for producing stated project deliverables (McConnel, 2011).
For successful delivery of the project product, the project manager should effectively estimate costs, track expenditure over time and adequately react to situations when the financial resources are over-spent or under-spent, or there are opportunities for savings in the project budget.
Estimating the cost – this is usually applied to project costs, resources, effort, and durations and is usually preceded by a modifier

## Slide 12: Elements of the Management Plan
Communication - You need to establish who will need to know the research findings and how will it be communicated to them. Ucdavis.edu (n.d.) state some key information needed for communicating – purpose, audience, date and occurrence, method of communication and responsible person.
Risk - A potential undesirable and unplanned event or circumstance, anticipated in advance, which could prevent the project from meeting one or more of its objectives.
  Issue -An event or circumstance that has occurred with project impact that needs to be managed and resolved, with escalation if appropriate.

## Slide 13: Sample Research Plan
Research Objectives | Related Activities | Resources required | Cost | Risk | Communication
Research Topic: Customer Service in Small Businesses
Hypothesis: Poor Customer Service causes small businesses increases operational cost.

## Slide 14: AC 2.1: Match resources efficiently to the research question or hypothesis M1 Produce a comprehensive project management plan, milestone schedule and project schedule for monitoring and completing the aims and objectives of the project.

## Slide 15: How do you monitor your Progress?
Before you can start analysing your data, you first have to collect it. What follows is a guide to creating the observational monitoring system that you will need to collect the data.
Collect data by completing event logs and other forms on a regular basis
Event logs are written accounts of the major activities of the initiative. They might also be used to record any changes in the community brought about by the initiative, such as new programs, policies, or practices related to the initiative's goals and mission.

## Slide 16: The Event Log
The event log might include important information such as:
  The month/day/year of the event
  A description of the event itself, including: ◦Why it was important
  What happened as a result
  A description of the details of the event, including: ◦Who was involved
  What organizations contributed people and resources
  What community sector or objective this relates to
  If this is the first time this event happened

## Slide 17: Research Project Milestones
Milestones - is an important date or event that you can include in your project sheets, reflected as a diamond symbol in your Gantt charts (Anthony, 2014). Milestones not only help your team stay on track, they are also useful to you as a project manager to more accurately determine whether or not your project is on schedule.
Incorporating milestones in your project planning helps you and your team keep sight of:
  Key Dates - complete interviews, complete date entry, board meetings, product rollouts and other key dates mark significant pieces of your project.

## Slide 18: Research Project Milestones
  Key Deadlines - are important to surface on large project plans so your team can easily see what’s coming up and plan accordingly. For example, the date that website development is completed or when customer conference registrations need to be returned to qualify for early bird pricing.
  External Dates and Deliveries - For example, a due date for a deliverable of a Report by an Agency, the date when you expect to receive the questionnaires from the printer. These key events can affect when other tasks in your project are allowed to start.

## Slide 19: Work Breakdown Structure
Based on the Project deliverables, you should create WBS. Create WBS is the process of subdividing project deliverables and project work into smaller, more manageable components. (PMBOK® Guide, Fifth Edition, Glossary)
Each deliverable or achievement must equal the sum of its sub-elements. The WBS can be represented either as a list or graphically (University of Calgary, 2016)

## Slide 20: Work Breakdown Structure
WBS for Building a Table: Table form
1. Table Designed 1.1 Dimensions determined 1.2 Drawings completed 2. Materials Obtained 2.1 Material calculated 2.2 Materials purchased 3. Table Constructed 3.1 Parts prepared 3.1.1 Top cut to size 3.1.2 Legs turned 3.1.3 Parts assembled 4. Table Finished 4.1 Table sanded 4.2 Table stained 5. Table installed

## Slide 21: Gantt Chart
A gantt chart is a time-tested tool for visually representing the steps, assignments, and duration in any project. So when project owners or managers kick off a new project, they'll look to create a Gantt chart first. It’s a useful way to keep track of all the moving pieces.

## Slide 23: References
Anthony, Kelly (2014) Gnatt Chart Tips: When to use a Milestone in a Project Plan retrieved from https://www.smartsheet.com/blog/support-tip-milestones-in-project-management
The Audience Agency (2012) How to Develop a Research Plan retrieved from http://www.culturehive.co.uk.gridhosted.co.uk/wp-content/uploads/2013/04/BD_Developing-a-Research-Plan.pdf
Ccdavis.edu (n.d.) Organisational Excellence PMP Kickoff retrieved fron January 27, 2017 from http://oe.ucdavis.edu/local_resources/docs/pmpkickoff.pdf
Pendolino, Mark (2015) How to Create a Project Timeline Using Microsoft Project retrieved from https://www.smartsheet.com/blog/how-create-project-timeline-using-microsoft-project
PMI (2008) PMBOK (Project Management Body of Knowledge) Guide, Fourth Edition
University of Calgary (2016) Work Breakdown Structure and Schedules retrieved from http://people.ucalgary.ca/~design/engg251/First%20Year%20Files/wbss.pdf
Write.com (n.d.) Making a Research Plan: How to Develop a Research Strategy retrieved on January 27, 2017 from http://www.write.com/writing-guides/research-writing/research-process/making-a-research-plan-how-to-develop-a-research-strategy/